## env_data
Environment | Category | Planned | start_date | end_date | summary
Development | Database | Yes | 2022-06-06 19:00 | 2022-06-07 | Upgrading Oracle to 19c. DEVL 142 and DEVL 942
Development | Database | Yes | 2022-06-06 19:30 | 2022-06-06 20:00 | Oracle Unified Directory replacement Radiant Logic
Clone UAT | Database | Yes | 2022-06-07 19:00 | 2022-06-08 | Oracle 19c upgrade Prod124_s and Prod124_t
Clone UAT | Application | No | 2022-06-07 10:28 | 2022-06-07 11:31 | Holdings Unavailable, app code issue
Clone Pre Prod | Database | Yes | 2022-06-07 19:00 | 2022-06-08 | Oracle 19c upgrade Prod124_s and Prod124_t
Clone UAT | Database | Yes | 2022-06-08 19:00 | 2022-06-09 | Oracle 19c upgrade Prod209
Clone Pre Prod | Database | Yes | 2022-06-08 19:00 | 2022-06-09 | Oracle 19c upgrade Prod209
Clone Pre Prod | Application | No | 2022-06-09 18:00 | 2022-06-09 18:37 | when trying to access FA Performance Summary, an error is being returned "No FA record Found
Clone UAT | Application | Yes | 2022-06-11 08:00 | 2022-06-12 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone Pre Prod | Application | Yes | 2022-06-11 | 2022-06-12 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Clone Pre Prod | Application | Yes | 2022-06-11 08:00 | 2022-06-12 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone UAT | Application | Yes | 2022-06-12 | 2022-06-13 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone Pre Prod | Application | Yes | 2022-06-12 | 2022-06-13 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Clone Pre Prod | Application | Yes | 2022-06-12 | 2022-06-13 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Development | Mainframe | No | 2022-06-13 13:44 | 2022-06-13 14:30 | Multiple Development CICS regions at end of memory, root cause was imperva security
Clone UAT | Application | Yes | 2022-06-13 | 2022-06-14 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone UAT | Database | Yes | 2022-06-13 19:00 | 2022-06-14 | Oracle 19C Upgrade to PROD017 & PROD317 - Account Access (CLONE) database
Clone Pre Prod | Application | Yes | 2022-06-13 | 2022-06-14 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Clone Pre Prod | Application | Yes | 2022-06-13 | 2022-06-14 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone Pre Prod | Application | Yes | 2022-06-13 19:00 | 2022-06-14 | Oracle 19C Upgrade to PROD017 & PROD317 - Account Access (CLONE) database
Clone UAT | Application | Yes | 2022-06-14 | 2022-06-14 09:30 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Clone Pre Prod | Application | Yes | 2022-06-14 | 2022-06-15 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Clone Pre Prod | Application | Yes | 2022-06-14 | 2022-06-14 09:30 | Broadridge QA, Clone Q/R, refresh will be the weekend of 6/11 – 6/12 and will impact testing on 6/13 – 6/14
Development | Developer Tools | Yes | 2022-06-15 21:00 | 2022-06-16 | Apply April 2022 Oracle PSU for WebLogic to DEV SANDBOX internal domains
Clone UAT | Application | Yes | 2022-06-15 19:00 | 2022-06-16 | PROD217_T & PROD217_S – Account Access (CLONE) application Outage Oracle 19c Upgrade
Clone Pre Prod | Application | Yes | 2022-06-15 | 2022-06-16 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Clone Pre Prod | Application | Yes | 2022-06-15 19:00 | 2022-06-16 | PROD217_T & PROD217_S – Account Access (CLONE) application Outage Oracle 19c Upgrade
Clone Pre Prod | Application | Yes | 2022-06-16 | 2022-06-16 23:59 | PeopleSoft HR (HRPROD – Pre Prod) Application & JAC Outage for People Tools Upgrade Project (Upgrade from PT8.58.09 to PT8.59.07)
Development | Application | Yes | 2022-06-17 19:00 | 2022-06-18 02:00 | Qlik Replicate and associated DB2 function will be upgraded to version 2021.11. All instances of Qlik will be upgraded at the same time due to version requirements between Qlik and the DB2 function during the 7pm - 2am outage window, Impact: Replication via Qlik will not be available during the upgrade. Replication will resume once the upgrade has been completed. A limited set of users will not be able to start/stop or modify their replication tasks during the upgrade. Apps which rely on the replication will not see any updates for the duration of the upgrade.
Development | Mainframe | Yes | 2022-06-21 21:30 | 2022-06-22 | Outage - IPL of Development Mainframe LPAR
Development | Linux Servers | Yes | 2022-06-21 05:00 | 2022-06-21 07:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Linux Servers | Yes | 2022-06-21 17:00 | 2022-06-21 19:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Mainframe | Yes | 2022-06-22 21:00 | 2022-06-23 | CA-7 batch will be on hold and EDJA will be shutdown and IPL'ed, Impact: Development mainframe, and ISPW and ISPW promotions to prod will be unavailable during the outage. Any promotions scheduled to release during the outage time will complete after EDJA is back up.
Development | Linux Servers | Yes | 2022-06-22 05:00 | 2022-06-22 07:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Linux Servers | Yes | 2022-06-22 10:00 | 2022-06-22 11:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Linux Servers | Yes | 2022-06-22 17:00 | 2022-06-22 19:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Clone UAT | Application | Yes | 2022-06-22 16:00 | 2022-06-22 22:00 | SYSTEM Software Maintenance - z/OS Toleration PTFs will be applied on Q9, Impact: There will be an IPL of Q9, Systems are not available between 4:00PM to 10:00PM
Clone Pre Prod | Application | Yes | 2022-06-22 16:00 | 2022-06-22 22:00 | SYSTEM Software Maintenance - z/OS Toleration PTFs will be applied on Q9, Impact: There will be an IPL of Q9, Systems are not available between 4:00PM to 10:00PM
Development | Developer Tools | No | 2022-06-23 06:03 | 2022-06-23 08:17 | Dev Paas Server - docker issue on paas-7
Development | Mainframe | Yes | 2022-06-23 | 2022-06-23 01:00 | CA-7 batch will be on hold and EDJA will be shutdown and IPL'ed, Impact: Development mainframe, and ISPW and ISPW promotions to prod will be unavailable during the outage. Any promotions scheduled to release during the outage time will complete after EDJA is back up.
Development | Linux Servers | Yes | 2022-06-23 05:00 | 2022-06-23 07:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Linux Servers | Yes | 2022-06-23 17:00 | 2022-06-23 19:00 | Linux Patching - After patching instant reboot may required, there is no full scale of outage not reported. Avg of outage to 30 mins
Development | Database | Yes | 2022-06-23 17:30 | 2022-06-24 | Oracle Server outage is required to test a fix for a production issue that caused multiple application outages include Online Access, Impact: Development Oracle Outage. All Oracle servers will be down from 7:30 PM CT, All application teams, please start shutting down your applications at 7:00PM in preparation for the server outage starting at 7:30PM CST. Also, have your applications started prior to 8 am CST Friday, July 24th.
Development | Database | Yes | 2022-06-24 | 2022-06-24 06:00 | Oracle Server outage is required to test a fix for a production issue that caused multiple application outages include Online Access, Impact: Development Oracle Outage. All Oracle servers will be down from 7:30 PM CT, All application teams, please start shutting down your applications at 7:00PM in preparation for the server outage starting at 7:30PM CST. Also, have your applications started prior to 8 am CST Friday, July 24th.
Clone UAT | Database | Yes | 2022-06-24 18:00 | 2022-06-24 21:00 | Oracle Cluster 1&2 outage to capacity for crash dumps, outage on nlpdora1-1, nlpdora1-2, nlpdora1-3, nlpdora1-4, nlpdora2-1, nlpdora2-2, nlpdora2-3, nlpdora2-4 in Clone is required to test a fix for a production issue that caused multiple application outages, include Online Access.
Clone Pre Prod | Database | Yes | 2022-06-24 18:00 | 2022-06-24 21:00 | Oracle Cluster 1&2 outage to capacity for crash dumps, outage on nlpdora1-1, nlpdora1-2, nlpdora1-3, nlpdora1-4, nlpdora2-1, nlpdora2-2, nlpdora2-3, nlpdora2-4 in Clone is required to test a fix for a production issue that caused multiple application outages, include Online Access.
Development | Mainframe | Yes | 2022-06-26 02:00 | 2022-06-26 12:00 | Mainframe Non-Production Environments are being migrated to an upgraded processor. Impact: All non-production environments (LPAR's) will be unavailable
Clone UAT | Mainframe | Yes | 2022-06-26 02:00 | 2022-06-26 12:00 | Z14 Mainframe Upgraded on UAT Pre Prod and Q9, Impact: All non-production environments (LPAR's) will be unavailable
Clone Pre Prod | Mainframe | Yes | 2022-06-26 02:00 | 2022-06-26 12:00 | Z14 Mainframe Upgraded on UAT Pre Prod and Q9, Impact: All non-production environments (LPAR's) will be unavailable
Clone UAT | Security | No | 2022-06-27 23:30 | 2022-06-28 | firewall upgrade change was blocking the ability for multifactor authentication to reach the cloud vendor to send text messages. Impact: Anyone trying to use powerbroker or login with privilege's to a Linux/windows servers
Clone UAT | Security | Yes | 2022-06-27 21:30 | 2022-06-27 23:59 | Clone Internet Firewall OS Upgrade, Impact: Batch and Autosys will be put on hold at 9:15pm and active batch jobs will be cancelled at 9:30pm. A brief interruption to the Clone internet may occur.
Clone Pre Prod | Security | No | 2022-06-27 23:30 | 2022-06-28 | firewall upgrade change was blocking the ability for multifactor authentication to reach the cloud vendor to send text messages. Impact: Anyone trying to use powerbroker or login with privilege's to a Linux/windows servers
Clone Pre Prod | Security | Yes | 2022-06-27 21:30 | 2022-06-27 23:59 | Clone Internet Firewall OS Upgrade, Impact: Batch and Autosys will be put on hold at 9:15pm and active batch jobs will be cancelled at 9:30pm. A brief interruption to the Clone internet may occur.
Development | Application | Yes | 2022-06-28 21:00 | 2022-06-29 | Outage - WebLogic PSU, Impact: Dev/Integ weblogic domains will be unavailable during this window.
Clone UAT | Security | No | 2022-06-28 | 2022-06-28 03:40 | firewall upgrade change was blocking the ability for multifactor authentication to reach the cloud vendor to send text messages. Impact: Anyone trying to use powerbroker or login with privilege's to a Linux/windows servers
Clone UAT | Security | Yes | 2022-06-28 | 2022-06-28 04:30 | Clone Internet Firewall OS Upgrade, Impact: Batch and Autosys will be put on hold at 9:15pm and active batch jobs will be cancelled at 9:30pm. A brief interruption to the Clone internet may occur.
Clone Pre Prod | Security | No | 2022-06-28 | 2022-06-28 03:40 | firewall upgrade change was blocking the ability for multifactor authentication to reach the cloud vendor to send text messages. Impact: Anyone trying to use powerbroker or login with privilege's to a Linux/windows servers
Clone Pre Prod | Security | Yes | 2022-06-28 | 2022-06-28 04:30 | Clone Internet Firewall OS Upgrade, Impact: Batch and Autosys will be put on hold at 9:15pm and active batch jobs will be cancelled at 9:30pm. A brief interruption to the Clone internet may occur.
Development | Application | Yes | 2022-06-29 | 2022-06-29 01:00 | Outage - WebLogic PSU, Impact: Dev/Integ weblogic domains will be unavailable during this window.
Development | Database | Yes | 2022-06-29 19:00 | 2022-06-29 21:00 | TFA upgrade to all Oracle database servers, Impact: 5 min outage to servers with OS Watcher
Clone UAT | Application | Yes | 2022-06-29 21:00 | 2022-06-29 23:59 | April 2022 WebLogic PSU- INTERNAL CLONE UAT. Web platform team will make sure all the UAT WebLogic domains will be up and running after the change. Impact: Clone UAT-STL environment will be unavailable during the change window.
Clone Pre Prod | Application | Yes | 2022-06-29 21:00 | 2022-06-29 23:59 | April 2022 WebLogic PSU- INTERNAL CLONE UAT. Web platform team will make sure all the UAT WebLogic domains will be up and running after the change. Impact: Clone UAT-STL environment will be unavailable during the change window.
Development | Application | Yes | 2022-06-30 19:00 | 2022-06-30 23:00 | Weblogic Server Patching, Impact: Servers impacted - nldgwladm-3, nldjweb-3, nldjweb-4, nldaweb-41, nldaweb-42, nldaweb-51, nldaweb-52, nldaweb-61, nldaweb-62, nldaweb-71, nldaweb-72, nldaweb-81, nldaweb-82, nldaweb-891, nldaweb-92, nldatrdweb-4, nldatrdweb-5, nldwlswebi-001, nldwlswebi-002. Servers will reboot
Clone UAT | Application | Yes | 2022-06-30 21:00 | 2022-06-30 23:59 | Apply April 2022 Oracle PSU for WebLogic to PRE-PROD CLONE internal domains. Web platform team will make sure all the Pre-prod STL WebLogic domains will be up and running after the change. Impact: Pre-prod -stl environment will be unavailable during this window.
Clone Pre Prod | Application | Yes | 2022-06-30 21:00 | 2022-06-30 23:59 | Apply April 2022 Oracle PSU for WebLogic to PRE-PROD CLONE internal domains. Web platform team will make sure all the Pre-prod STL WebLogic domains will be up and running after the change. Impact: Pre-prod -stl environment will be unavailable during this window.
Clone UAT | Security | Yes | 2022-07-05 19:00 | 2022-07-05 19:30 | Clone INET Firewall / MFA troubleshooting: During the outage, users attempting to powerbroker to root or log into a windows servers may not receive the required 4 digit Multifactor Authentication text message.
Clone Pre Prod | Security | Yes | 2022-07-05 19:00 | 2022-07-05 21:00 | Clone INET Firewall / MFA troubleshooting: During the outage, users attempting to powerbroker to root or log into a windows servers may not receive the required 4 digit Multifactor Authentication text message.
Clone UAT | Windows Servers | Yes | 2022-07-07 13:00 | 2022-07-07 16:00 | Autosys Agent Upgrade for Windows Servers: During the outage, the following servers may experience intermittent job failures and delays in the schedule for jobs running on the following servers. affected servers: nwpviztool-001,nwpviztool-002,nwpviztool-003,nwpviztool-004, nwppsoftfsu-001, twpperf-01, nwpperf-01, twptools-01, nwpscac-03, nwppsofthr-001, nwppsofthru-001,twpscac-03, twpscac-01, nwptools-01
Clone UAT | Network | Yes | 2022-07-07 21:30 | 2022-07-07 22:30 | Remove the Gigamon from between the Internet routers and the LER router. Redundant lines so not a true outage.
Clone UAT | Web Servers | No | 2022-07-07 17:00 | 2022-07-07 23:59 | complianceWeb-func domain is down, issues with data source changes
Clone Pre Prod | Windows Servers | Yes | 2022-07-07 13:00 | 2022-07-07 16:00 | Autosys Agent Upgrade for Windows Servers: During the outage, the following servers may experience intermittent job failures and delays in the schedule for jobs running on the following servers. affected servers: nwpviztool-001,nwpviztool-002,nwpviztool-003,nwpviztool-004, nwppsoftfsu-001, twpperf-01, nwpperf-01, twptools-01, nwpscac-03, nwppsofthr-001, nwppsofthru-001,twpscac-03, twpscac-01, nwptools-01
Clone Pre Prod | Network | Yes | 2022-07-07 21:30 | 2022-07-07 22:30 | Remove the Gigamon from between the Internet routers and the LER router. Redundant lines so not a true outage.
Clone Pre Prod | Web Servers | No | 2022-07-07 17:00 | 2022-07-07 23:59 | finHRWeb-phx domain is down, no resolution yet
Development | Database | Yes | 2022-07-08 19:00 | 2022-07-08 21:00 | Oracle client upgrade to 19c on nldgtools-9: Outage to the application while the Oracle 12c client uninstall and then install the Oracle 19c client
Clone UAT | Web Servers | No | 2022-07-08 00:01 | 2022-07-08 09:55 | Oracle client upgrade to 19c on nldgtools-9: Outage to the application while the Oracle 12c client uninstall and then install the Oracle 19c client
Clone Pre Prod | Web Servers | No | 2022-07-08 00:01 | 2022-07-08 12:55 | finHRWeb-phx domain is down, no resolution yet
Clone UAT | Application | Yes | 2022-07-11 | 2022-07-11 23:59 | Broadridge QA, Clone Q/R, refresh will be the weekend of 7/9 – 7/10 and will impact testing on 7/11 – 7/12
Clone Pre Prod | Application | Yes | 2022-07-11 | 2022-07-11 23:59 | Broadridge QA, Clone Q/R, refresh will be the weekend of 7/9 – 7/10 and will impact testing on 7/11 – 7/12
Clone UAT | Application | Yes | 2022-07-12 | 2022-07-12 08:00 | Broadridge QA, Clone Q/R, refresh will be the weekend of 7/9 – 7/10 and will impact testing on 7/11 – 7/12
Clone Pre Prod | Application | Yes | 2022-07-12 | 2022-07-12 08:00 | Broadridge QA, Clone Q/R, refresh will be the weekend of 7/9 – 7/10 and will impact testing on 7/11 – 7/12
Clone UAT | Application | Yes | 2022-07-13 19:00 | 2022-07-13 22:00 | Web-Platform will upgrade the following WebLogic domains to wls12214 in UAT application2SvcA application2SvcB attachmentSvcA attachmentSvcB contactSvcA contentFwkSvcA contentFwkSvcB quotesSvcB supportSvcHQWweb supportSvcWeb testWeb Impact: The listed domains in UAT will experience an outage.
Clone UAT | Database | Yes | 2022-07-13 19:00 | 2022-07-13 22:00 | Oracle Crash Dump Configuration Impact: Outage to the following Oracle databases PROD007 – EDW (Data Warehouse) PROD044 – Statements PROD047 – AutoSys PROD095 – APEX Stage PROD113 – HQ Consolidated PROD233 – Asset Center (Pre-Prod)
Clone Pre Prod | Database | Yes | 2022-07-13 19:00 | 2022-07-13 21:00 | Oracle Crash Dump Configuration Impact: Outage to the following Oracle databases PROD007 – EDW (Data Warehouse) PROD044 – Statements PROD047 – AutoSys PROD095 – APEX Stage PROD113 – HQ Consolidated PROD233 – Asset Center (Pre-Prod)
Clone UAT | Database | Yes | 2022-07-14 19:00 | 2022-07-14 21:00 | Oracle Crash Dump Configuration Impact: Outage to the following Oracle databases MGMT025 – OEM PROD017 – Account Access (UAT TPE) PROD033 – Asset Manager (UAT) PROD035 – Obfuscation PROD036 – IRP PROD050 – Service Center (UAT) PROD064 – WAM (TPE) PROD072 – PS HR (UAT/Upgrade) PROD073 – PS Fin (UAT/Upgrade) PROD086 – OIM Admin PROD106 – Bondnet (UAT) PROD110 – AutoSys (Q9) PROD124 – CFW (TPE) PROD209 – ENT (UAT2) PROD215 – ECM (UAT) PROD217 – Online Access (Pre-Prod TPE) PROD224 – CFW (UAT) PROD247 – AutoSys (Pre-Prod) PROD285 – OIM (UAT) PROD906 – Bondnet (Q9)
Clone Pre Prod | Database | Yes | 2022-07-14 19:00 | 2022-07-14 21:00 | Oracle Crash Dump Configuration Impact: Outage to the following Oracle databases MGMT025 – OEM PROD017 – Account Access (UAT TPE) PROD033 – Asset Manager (UAT) PROD035 – Obfuscation PROD036 – IRP PROD050 – Service Center (UAT) PROD064 – WAM (TPE) PROD072 – PS HR (UAT/Upgrade) PROD073 – PS Fin (UAT/Upgrade) PROD086 – OIM Admin PROD106 – Bondnet (UAT) PROD110 – AutoSys (Q9) PROD124 – CFW (TPE) PROD209 – ENT (UAT2) PROD215 – ECM (UAT) PROD217 – Online Access (Pre-Prod TPE) PROD224 – CFW (UAT) PROD247 – AutoSys (Pre-Prod) PROD285 – OIM (UAT) PROD906 – Bondnet (Q9)
Development |  | No | 2022-07-15 08:14 | 2022-07-15 08:47 | Unable to access the Dev Firecall from last 10 min. PFA
Clone UAT | Application | Yes | 2022-07-15 15:00 | 2022-07-16 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application
Clone UAT | Database | No | 2022-07-15 06:00 | 2022-07-15 13:30 | Connectivity issues to Oracle prod2152 impacting various web domains and applications, Root Cause: DBAs are still researching root cause.
Clone Pre Prod | Application | Yes | 2022-07-15 15:00 | 2022-07-16 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application
Clone UAT | Database | Yes | 2022-07-16 | 2022-07-17 | Outage to PROD147 database and OIC application on UAT and Pre Prod, Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 15th starting at 3:00PM throughout the weekend
Clone Pre Prod | Database | Yes | 2022-07-16 12:00 | 2022-07-17 | Outage to PROD147 database and OIC application on UAT and Pre Prod, Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 15th starting at 3:00PM throughout the weekend
Clone UAT | Database | Yes | 2022-07-17 | 2022-07-17 08:00 | Outage to PROD147 database and OIC application on UAT and Pre Prod, Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 15th starting at 3:00PM throughout the weekend
Clone Pre Prod | Database | Yes | 2022-07-17 | 2022-07-17 08:00 | Outage to PROD147 database and OIC application on UAT and Pre Prod, Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 15th starting at 3:00PM throughout the weekend
Clone UAT | Application | Yes | 2022-07-18 19:00 | 2022-07-18 23:00 | RHEL OS patch to WebLogic internal servers in UAT All WebLogic internal servers will be patched with the latest RHEL patch Impact: All UAT WebLogic domains will experience an outage.
Clone UAT | Database | Yes | 2022-07-18 07:00 | 2022-07-19 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Clone Pre Prod | Database | Yes | 2022-07-18 07:00 | 2022-07-19 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Clone UAT | Application | Yes | 2022-07-19 21:05 | 2022-07-19 22:05 | Outage to the CA7ONL started task on UAT, IMPACT: No new batch will run during this time and QCL IDs will not be able to access CA-7 during this time
Clone UAT | Database | Yes | 2022-07-19 | 2022-07-20 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Clone Pre Prod | Database | Yes | 2022-07-19 | 2022-07-20 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Development | Mainframe | Yes | 2022-07-20 21:30 | 2022-07-21 | Z/OS 2.4 Upgrade on EDJA - Development Impact: EDJA will be unavailable on 7/20 from 9:30PM until 2:00AM on 7/21. This is to support the Z/OS 2.4 Upgrade on the Mainframe
Development | Application | No | 2022-07-20 08:28 | 2022-07-20 10:29 | Identified that the ACF2id,wlsdev, was locked out. Impact - Some Fwk 3.0 apps like holdings, portfolio, statements, fast, quotes, etc in Development were not working because a few WebLogic domains (application2Svc,quotesWeb,fastWeb,branchSvcWeb) were in a failed state and couldn't start up. It was failing to start because the businessDataSrc couldn't connect to DB2. The businessDataSrc uses the id wlsdev to connect to DB2 and with wlsdev locked out the domain would not start. FWK 4.0 apps running in dev and local machine using wlsdev. Colleen worked with User Access to get the id unlocked while the Web Platform team started up the WebLogic domains. However, this took multiple times as the id still got locked. When all the WebLogic domains finally started that was around 10:29am. The developers were reporting things were fixed, but the id still kept getting locked out. Fix: There was a Zoom bridge with the Dev team, Web Platform, Platform As a Service, and a MF person to identify where the Lock was originating from. It was determined that it was coming from a Konvoy server. The Platform As a Service team was then able to determine which application was using wlsdev and shut it down by 12:00pm. Notified the user and told them to stop using wlsdev.
Clone UAT | Database | Yes | 2022-07-20 | 2022-07-20 07:00 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Clone UAT | Mainframe | Yes | 2022-07-20 21:30 | 2022-07-21 | 2022 z/OS 2.4 Upgrade on the Mainframe will install a new version of z/OS. The z/OS is the Operating System that controls the Mainframe. Since this is a completely new version of z/OS it would be in the best interest of each Application running on the Mainframe to have testers assigned to cover this install into each environment to verify that there are no issues to an application
Clone Pre Prod | Database | Yes | 2022-07-20 | 2022-07-20 07:00 | Outage to PROD147 database and OIC application on UAT and Pre Prod Impact: Compensation users will not be able to connect to PROD147 database or login to OIC application When: July 18th starting at 7:00AM – July 20th at 7:00AM
Clone Pre Prod | Application | Yes | 2022-07-20 19:00 | 2022-07-20 23:00 | RHEL OS patch to WebLogic internal servers in Pre-prod All WebLogic internal servers will be patched with the latest RHEL patch Impact: All Pre-prod WebLogic domains will experience an outage. Pre-prod Servers: nlpgwladm-2; nlpaweb-41, 42, 51, 52, 61, 62, 71, 72, 81, 82, 91, 92; nlpatrdweb-4,5 nlpasweb-41, 42, 51, 52, 61, 62, 71, 72, 81, 82, 91, 92; nlpastrdweb-4,5
Clone Pre Prod | Mainframe | Yes | 2022-07-20 21:30 | 2022-07-21 | 2022 z/OS 2.4 Upgrade on the Mainframe will install a new version of z/OS. The z/OS is the Operating System that controls the Mainframe. Since this is a completely new version of z/OS it would be in the best interest of each Application running on the Mainframe to have testers assigned to cover this install into each environment to verify that there are no issues to an application
Development | Mainframe | Yes | 2022-07-21 | 2022-07-21 02:00 | Z/OS 2.4 Upgrade on EDJA - Development Impact: EDJA will be unavailable on 7/20 from 9:30PM until 2:00AM on 7/21. This is to support the Z/OS 2.4 Upgrade on the Mainframe
Development | Application | No | 2022-07-21 11:37 | 2022-07-21 12:25 | Developer via Outage channel reported issues with wlsdev being locked again. Impact - Appeared to affect FWK 4.0 apps running in dev and local machine using wlsdev. WebLogic domains were fine since they were up and running and already have an established connection to DB2. Fix: Reached out to User Access to clear violations, but they reported by 12:25pm that it was not locked. Someone else must have unlocked the id.
Development | Application | No | 2022-07-21 15:59 | 2022-07-21 16:51 | Developer via Outages channel reported wlsdev can't connect. Impact - Appeared to affect FWK 4.0 apps running in dev and local machine using wlsdev. WebLogic domains were fine since they were up and running and already have an established connection to DB2. Fix: The PaaS Team identified another application using wlsdev. Root Cause:Application teams are using wlsdev in their FWK 4.0 applications to connect their applications to DB2 and most likely has an incorrect password to keep locking the id out. The ACF2id, wlsdev, is only supposed to be used within Fwk 3.0 applications. FWK 4.0 applications teams are supposed to create their own acf2id to connect to DB2. It appears the process is not get followed. I had the Dev Team send out a dev-alert reminding developers as well as mentioning it in the DevOps channel. Also, there will be an update about it in the DevOps Announcement today
Clone UAT | Mainframe | Yes | 2022-07-21 | 2022-07-21 02:15 | 2022 z/OS 2.4 Upgrade on the Mainframe will install a new version of z/OS. The z/OS is the Operating System that controls the Mainframe. Since this is a completely new version of z/OS it would be in the best interest of each Application running on the Mainframe to have testers assigned to cover this install into each environment to verify that there are no issues to an application
Clone Pre Prod | Mainframe | Yes | 2022-07-21 | 2022-07-21 02:15 | 2022 z/OS 2.4 Upgrade on the Mainframe will install a new version of z/OS. The z/OS is the Operating System that controls the Mainframe. Since this is a completely new version of z/OS it would be in the best interest of each Application running on the Mainframe to have testers assigned to cover this install into each environment to verify that there are no issues to an application
Clone Pre Prod | Application | Yes | 2022-07-21 21:05 | 2022-07-21 22:05 | Outage to the CA7ONL started task on Pre-Prod WHEN: Thursday, July 21st from 9:05PM – 10:05PM IMPACT: No new batch will run during this time and QCL IDs will not be able to access CA-7 during this time
Development | Application | No | 2022-07-22 08:39 | 2022-07-22 09:34 | APEX Outage
Clone UAT | Application | No | 2022-07-22 08:39 | 2022-07-22 09:34 | APEX Outage
Clone Pre Prod | Application | No | 2022-07-22 08:39 | 2022-07-22 09:34 | APEX Outage
Clone Pre Prod | Database | Yes | 2022-07-24 08:00 | 2022-07-24 13:00 | PROD009(Clone) – ENT Pre-Prod database will be upgraded to Oracle 19c. Impact – During this timeframe the following applications will experience an outage of up to five hours: PROD009(Clone) – ENT Pre-Prod applications Contact – Dan Humiston
Clone UAT | Clone | Yes | 2022-07-25 19:00 | 2022-07-25 23:59 | Clone Active Directory will now read from UAT Peoplebase What: To reduce data discrepancies, reduce duplicate HR Hire work and improve contractor hiring and access the Peoplebase to AD sync job will now pull from UAT Peoplebase instead of Preprod Peoplebase. Impact: As a result of the change AD account attributes like phone number and names will now reflect the value in UAT Peoplebase which is regularly refreshed from production data. This should bring the data in clone AD better in-line with production. If you are working with any user account data which has been purposefully modified in clone AD or Preprod PeopleBase for testing purpose, please reach out to the contact below so we can explore maintaining your changes through the deployment. Contact: Grace Lin, Tech IAM Developers
Clone UAT | Linux Servers | Yes | 2022-07-26 19:00 | 2022-07-26 21:00 | RHEL 7 202206 patch ECM Servers - UAT What: OS Patches for UAT ECM servers: nlpgsecm-5u, nlpgecm-5u, nlpgsecm-6u, nlpgecm-6u, nlpawcmpts-2u Impact: Outage to UAT ECM ecmdoc ecmbrsrv ecmcomm ecmrpt ecmarchive ecmworm ecmwflow ecmstmt Contact: John Stewart
Clone UAT | Application | Yes | 2022-07-26 19:00 | 2022-07-26 21:00 | Enable WebLogic Rest Mgmt API -various UAT, Preprod STL and PHX domains impacted What: Restart domains to enable WebLogic Rest management API Impact: Various domains will be restarted in UAT Contact: Praht Dooley Domain list: UAT: userProvisionWeb-fun
Clone UAT | Application | Yes | 2022-07-26 21:30 | 2022-07-27 | DXC will be IPLing UAT (EJQ1) to set up new SYSRES volumes in preparation for z/OS 2.4 Upgrade What: DXC will be IPLing UAT (EJQ1) to set up new SYSRES volumes in preparation for z/OS 2.4 Upgrade Impact: UAT (EJQ1) will be unavailable during the outage. Contact: Michael Buechlein
Clone Pre Prod | Application | Yes | 2022-07-26 19:00 | 2022-07-26 21:00 | Enable WebLogic Rest Mgmt API -various UAT, Preprod STL and PHX domains impacted What: Restart domains to enable WebLogic Rest management API Impact: Various domains will be restarted in Preprod STL and PHX – full list below Contact: Praht Dooley Domain list: PP STL: attachmentSvcA-stl, applicationSvcA-stl, application2SvcA-stl, clientReportingSvcA-stl, common2SvcA-stl, clientReportingWeb-stl, commonSvcA-stl, commonSvcA-stl, complianceWeb2-stl, common3SvcA-stl, contactSvcA-stl, complianceWeb-stl, contentFwkSvcA-stl, opsWeb-stl, opsWeb2-stl, opsWeb3-stl, portfolioWeb-stl, proposalWeb-stl, supportSvcHQWeb-stl, supportSvcWeb-stl, testWeb-stl, userProvisionWeb-stl, vendorAuthWeb-stl, PP PHX: application2SvcA-phx, alertsWeb-phx, accountAccessWeb-phx, accountSvcA-phx, accountWeb-phx, attachmentWeb-phx, branchSvcWeb-phx, bondOrderWeb-phx, commonSvcA-phx, clientReportingSvcA-phx, complianceWeb-phx, commonSvcA-phx, complianceWeb2-phx, clientReportingWeb-phx, contactSvcA-phx, deviceMgmtSvcA-phx, contentWeb-phx, faPerfWeb-phx, equityOrderWeb-phx, iaaWeb-phx, insAnnuityWeb-phx, infraSvcA-phx, logonWeb-phx, insuredBankingWeb-phx, marketingWeb-phx, mfdOrderWeb-phx, opsWeb2-phx, portfolioWeb-phx, pubStageWeb-phx, serviceRequestWeb-phx, sslWeb-phx, supportSvcHQWeb-phx, supportSvcWeb-phx, tradesSvcA-phx, uitOrderWeb-phx, tradingSvcWeb2-phx, tradingSvcWeb-phx, userUtilityWeb-phx
Development | Application | Yes | 2022-07-27 08:00 | 2022-07-27 12:00 | Outage - IDMS Abandonment Cluster 13 moving to Devl What: IDMS Abandonment Cluster 13 moving to Devl Impact: These IDMS databases will be made read only during the outage: Income Distribution, Payment Schedule and Call Event Detail Databases. Cluster 13 records affected: CAEVNT-1451 CAMANDTL-1483 DISEVNT-1405 EVNTDTL-1462 IDSDIST-1404 ISUENO4-1403 PMTSCHD-1406 Contact: Lisa Baugh (IDMSAbandonment-CoreTeam) Post Implementation Checklist: Make sure that all code made it to the target environment - Pull up ICNVRT panel. Then type VERIFY_PGM_MOVE and hit enter. Enter in the target environment (EJQ1, EJQ2, etc…) and hit enter. Review output. This verifies the programs moved.
Clone UAT | Application | Yes | 2022-07-27 | 2022-07-27 00:30 | DXC will be IPLing UAT (EJQ1) to set up new SYSRES volumes in preparation for z/OS 2.4 Upgrade What: DXC will be IPLing UAT (EJQ1) to set up new SYSRES volumes in preparation for z/OS 2.4 Upgrade Impact: UAT (EJQ1) will be unavailable during the outage. Contact: Michael Buechlein
Development | Application | Yes | 2022-07-28 19:00 | 2022-07-28 21:00 | nldatrade-3 Firmware update What: nldatrade-3 needs to have a OneView profile applied and its firmware updated to remediate vulnerability incident INC0331441 Impact: Should be low impact. The server needs to be completely offline and risk is fairly low, but sometimes we get physical hardware that misbehaves when we shut servers like this down. Applying server OneView hardware profiles is SOP. Contact: Jason Keeton
Clone UAT | Linux Servers | Yes | 2022-07-28 19:00 | 2022-07-28 21:00 | Oracle 19c upgrade on nlpgtools-9/10 Removing Oracle 12c and 18c and upgrading to 19c. Details coming in workflow What: Upgrade Oracle client to 19c 64bit on the following Linux servers below in clone: nlpgtools-9 ejvoracli12r7x-12.1.0-7.el7.x86_64 nlpgtools-10 ejvoracli18r7x-18.3.0-7.el7.x86_64 nlpgtools-10 ejvoracli12r7x-12.1.0-7.el7.x86_64 nlpgtools-10 ejvoracli18r7i-18.3.0-5.el7.i686 nlpgtools-10 ejvoracli12r7i-12.2.0-8.el7.i686 Impact: Outage to the application during Oracle 19c client upgrade (1-2 hours) Both Oracle 12c 32bit & 64bit and 18c 32bit & 64bit client will be removed and point to 19c 64bit. APP OWNER ACTION Please update configuration files with the new Oracle 19c home and TNS_ADMIN if there is any hard code value relate to them ORACLE_HOME=/opt/oracle/product/19.3.x TNS_ADMIN=/opt/oracle/local/sqlnet Contact: Tina Cheng
Clone Pre Prod | Linux Servers | Yes | 2022-07-28 19:00 | 2022-07-28 22:00 | RHEL 7 202206 patch ECM and WCM Servers - Preprod What: OS Patches for Preprod ECM servers: nlpgecm-5, nlpgecm-7, nlpgecm-9, nlpgsecm-5, nlpgsecm-7, nlpgsecm-9, nlpecm-001, nlpecm-003 nlpecm-005, nlpswebecm-001, nlpswebecm-003, nlpswebecm-005, nlpgecm-6, nlpgecm-8, nlpgecm-10, nlpgsecm-6, nlpgsecm-6, nlpgsecm-10, nlpecm-002, nlpecm-004, nlpswebecm-002, nlpswebecm-004, nlpawcmpt-2, nlpecmadm-001 Impact: Outage to UAT ECM ecmdoc, ecmbrsrv, ecmcomm, ecmrpt, ecmarchive, ecmworm, ecmwflow, ecmstmt, Contact: John Stewart
Clone UAT | Database | Yes | 2022-08-01 08:00 | 2022-08-01 12:00 | UAT IDMS Cluster #13 What: IDMS Abandonment Cluster 13 moving to UAT Impact: These IDMS databases will be made read only during the outage: Income Distribution, Payment Schedule and Call Event Detail Databases. Cluster 13 records affected: CAEVNT-1451 CAMANDTL-1483 DISEVNT-1405 EVNTDTL-1462 IDSDIST-1404 ISUENO4-1403 PMTSCHD-1406 Contact: IDMSAbandonment-CoreTeam
Development | Application | Yes | 2022-08-02 19:00 | 2022-08-02 22:00 | DEV - Install patch on external domains. nldjweb3/4. aaSvcA-integ accountAccessWeb-integ attachmentWeb-integ iaaWeb-integ Impact: aaSvcA-integ accountAccessWeb-integ attachmentWeb-integ iaaWeb-integ Above domains will be impacted. We will make sure these domains are up and running after the patch. Contact: Kiran Chada
Development | Mainframe | Yes | 2022-08-03 21:00 | 2022-08-04 | Mainframe Outage - DXC IPL of EDJA ​system catalog reorg What: CA-7 batch will be on hold and EDJA will be shutdown and IPL'ed. This is for a Reorg catalog named SYS5DCAT.URUN.VSA0C01 to relieve capacity issue Impact: EDJA will be unavailable on 08/03 from 9:00PM until 02:00AM on 08/04. Batch will be held. (Any scheduled promotions in this time frame will be delayed until after we come back up) Contact: Mike Buechlein
Development | Application | No | 2022-08-03 10:44 | 2022-08-04 | Issue: connection timeouts on ALL calls from My Priorities and Starting Point (running on the DCOS DCX (critical) cluster) to any services running on the DCOS general cluster via the SSL offload farm (e.g., calls to crt-client-teams-rest-ssl, hrm-persons-svc-ssl, iaa-ejauthsvc-ssl, etc.). Fix/Root Cause: we added the new egress entry to allow communication to the Konvoy general cluster via the ssl farm to our network policy files, we were able to successfully connect to services running on the general cluster. This was required because the services on the general cluster that we could not connect to earlier have been migrated from DCOS to Konvoy. FYI, team is making a prod change this weekend to ensure that it doesn't bite them there too.
Development | Dev | Yes | 2022-08-03 17:00 | 2022-08-03 19:00 | Jumbo Frames enablement in Dev (Network work on nedsrv84) What: Maintenance on Oracle VM host nedsrv84 to modify the MTU – the following servers will be migrated to another host while this work is happening nldtestkj-001 nlddora1-4 nlddora2-3 nlddora2-5 Impact: Servers will be migrated to a different host while the work is being performed so no impact is expected. However issues have been noted with previous vMotions of Oracle servers if the servers are extremely busy. Contact: Jim Moore, 58453
Clone UAT | Clone | Yes | 2022-08-03 20:00 | 2022-08-03 23:00 | Clone Cisco Firepower IPS reboot The reboot will cause an outage to ALL clone branches. What: Clone Cisco Firepower IPS reboot When: August 3rd from 8:00PM – 11:00PM Impact: Loss of connectivity with Clone branches Contact: Eric Williams – 636.579.7430
Clone UAT | Application | No | 2022-08-03 10:44 | 2022-08-04 | Issue: connection timeouts on ALL calls from My Priorities and Starting Point (running on the DCOS DCX (critical) cluster) to any services running on the DCOS general cluster via the SSL offload farm (e.g., calls to crt-client-teams-rest-ssl, hrm-persons-svc-ssl, iaa-ejauthsvc-ssl, etc.). Fix/Root Cause: we added the new egress entry to allow communication to the Konvoy general cluster via the ssl farm to our network policy files, we were able to successfully connect to services running on the general cluster. This was required because the services on the general cluster that we could not connect to earlier have been migrated from DCOS to Konvoy. FYI, team is making a prod change this weekend to ensure that it doesn't bite them there too.
Clone Pre Prod | Application | Yes | 2022-08-03 19:00 | 2022-08-03 23:00 | WebLogic upgrades - Pre Prod What: Web-Platform will upgrade the following PreProd WebLogic domains to wls12214 application2SvcA applicationSvcA attachmentSvcA clientReportingSvcA clientReportingWeb commonSvc common2Svc common3Svc complianceWeb compliancWeb2 contactSvcA contentFwkSvcA opsWeb opsWeb2 opsWeb3 portfolioWeb proposalWeb supportSvcHQWeb supportSvcWeb testWeb vendorAuthWeb Impact: The listed domains in Preprod will experience an outage and any domain cluster routed to a listed Svc domain will be impacted too. Contact: Colleen Schoenfeld or Ravi Chintala
Clone Pre Prod | Clone | Yes | 2022-08-03 20:00 | 2022-08-03 23:00 | Clone Cisco Firepower IPS reboot The reboot will cause an outage to ALL clone branches. What: Clone Cisco Firepower IPS reboot When: August 3rd from 8:00PM – 11:00PM Impact: Loss of connectivity with Clone branches Contact: Eric Williams – 636.579.7430
Development | Mainframe | Yes | 2022-08-04 | 2022-08-04 02:00 | Mainframe Outage - DXC IPL of EDJA ​system catalog reorg What: CA-7 batch will be on hold and EDJA will be shutdown and IPL'ed. This is for a Reorg catalog named SYS5DCAT.URUN.VSA0C01 to relieve capacity issue Impact: EDJA will be unavailable on 08/03 from 9:00PM until 02:00AM on 08/04. Batch will be held. (Any scheduled promotions in this time frame will be delayed until after we come back up) Contact: Mike Buechlein
Development | Database | Yes | 2022-08-04 17:00 | 2022-08-04 20:00 | Maintenance will be done on Oracle host nedsrv84 The following VMs are on this host: Nldtestkj-001 Tlpdora1-5 Nlddora1-4 Nlddora2-3 Nlddora2-5 Impact: We do not anticipate any impact but this there have been issues in the past with vMotioning Oracle VMs off of a host. This is also the first deployment of the increased MTU. Contact: Jim Moore
Development | Application | Yes | 2022-08-04 19:00 | 2022-08-04 20:00 | Testing ansible to resume suspended datasources on nldaweb-41 Impact: Instance 1 on these domains will be unavailable accountSvcA-integ accountWeb-integ alertsWeb-integ applicationSvcA-integ branchSvcWeb-integ clientReportingWeb-integ commonSvcA-integ complianceWeb-integ faCompWeb-integ Contact: Praht Dooley
Development | Application | No | 2022-08-04 | 2022-08-04 01:37 | Issue: connection timeouts on ALL calls from My Priorities and Starting Point (running on the DCOS DCX (critical) cluster) to any services running on the DCOS general cluster via the SSL offload farm (e.g., calls to crt-client-teams-rest-ssl, hrm-persons-svc-ssl, iaa-ejauthsvc-ssl, etc.). Fix/Root Cause: we added the new egress entry to allow communication to the Konvoy general cluster via the ssl farm to our network policy files, we were able to successfully connect to services running on the general cluster. This was required because the services on the general cluster that we could not connect to earlier have been migrated from DCOS to Konvoy. FYI, team is making a prod change this weekend to ensure that it doesn't bite them there too.
Clone UAT | Database | Yes | 2022-08-04 19:00 | 2022-08-04 21:00 | Oracle 19c upgrade on nlpgtools-11/12/10p Removing Oracle 12c and 18c and upgrading to 19c. Details coming in workflow What: Upgrade Oracle client to 19c 64bit on the following Linux servers below in clone: tlpgtools-9 tlpgtools-10 tlpgtools-11 nlpgtools-11 nlpgtools-12 nlpgtools-11p nlpgtools-12p tlpgtools-12 Impact: Outage to the application during Oracle 19c client upgrade (1-2 hours) Both Oracle 12c 32bit & 64bit and 18c 32bit & 64bit client will be removed and then point to 19c 64bit. --64bit ejvoracli12r7x-12.1.0-7.el7.x86_64 ejvoracli12r7x-12.2.0-3.el7.x86_64 ejvoracli18r7x-18.3.0-7.el7.x86_64 -- 32bit: ejvoracli18r7i-18.3.0-5.el7.i686.rpm ejvoracli12r7i-12.2.0-8.el7.i686.rpm ejvoracli12r7i-12.1.0-4.el7.i686.rpm APP OWNER ACTION Please update configuration files with the new Oracle 19c home and TNS_ADMIN if there is any hard code value relate to them ORACLE_HOME=/opt/oracle/product/19.3.x TNS_ADMIN=/opt/oracle/local/sqlnet Contact: Tina Cheng
Clone UAT | Application | Yes | 2022-08-04 21:30 | 2022-08-05 | IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install What: IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install Impact: EJQ2 will be unavailable during the outage. Contact: Michael Buechlein
Clone UAT | Application | No | 2022-08-04 | 2022-08-05 | Issue: connection timeouts on ALL calls from My Priorities and Starting Point (running on the DCOS DCX (critical) cluster) to any services running on the DCOS general cluster via the SSL offload farm (e.g., calls to crt-client-teams-rest-ssl, hrm-persons-svc-ssl, iaa-ejauthsvc-ssl, etc.). Fix/Root Cause: we added the new egress entry to allow communication to the Konvoy general cluster via the ssl farm to our network policy files, we were able to successfully connect to services running on the general cluster. This was required because the services on the general cluster that we could not connect to earlier have been migrated from DCOS to Konvoy. FYI, team is making a prod change this weekend to ensure that it doesn't bite them there too.
Clone UAT | Application | No | 2022-08-04 08:00 | 2022-08-04 09:30 | Jones link unavailable to do an ASM change that occurred. Root cause: Automatic update to the policy in both clone and prod impacting web pages
Clone UAT | Clone | Yes | 2022-08-04 17:00 | 2022-08-04 18:00 | Jumbo Frames enablement in clone (Network work on nedsrv84) What: Maintenance on Oracle VM host nedsrv84 to modify the MTU – the following servers will be migrated to another host while this work is happening tlpdora1-5 Impact: Servers will be migrated to a different host while the work is being performed so no impact is expected. However issues have been noted with previous vMotions of Oracle servers if the servers are extremely busy. Contact: Jim Moore, 58453
Clone Pre Prod | Database | Yes | 2022-08-04 19:00 | 2022-08-04 21:00 | Oracle 19c upgrade on nlpgtools-11/12/10p Removing Oracle 12c and 18c and upgrading to 19c. Details coming in workflow What: Upgrade Oracle client to 19c 64bit on the following Linux servers below in clone: tlpgtools-9 tlpgtools-10 tlpgtools-11 nlpgtools-11 nlpgtools-12 nlpgtools-11p nlpgtools-12p tlpgtools-12 Impact: Outage to the application during Oracle 19c client upgrade (1-2 hours) Both Oracle 12c 32bit & 64bit and 18c 32bit & 64bit client will be removed and then point to 19c 64bit. --64bit ejvoracli12r7x-12.1.0-7.el7.x86_64 ejvoracli12r7x-12.2.0-3.el7.x86_64 ejvoracli18r7x-18.3.0-7.el7.x86_64 -- 32bit: ejvoracli18r7i-18.3.0-5.el7.i686.rpm ejvoracli12r7i-12.2.0-8.el7.i686.rpm ejvoracli12r7i-12.1.0-4.el7.i686.rpm APP OWNER ACTION Please update configuration files with the new Oracle 19c home and TNS_ADMIN if there is any hard code value relate to them ORACLE_HOME=/opt/oracle/product/19.3.x TNS_ADMIN=/opt/oracle/local/sqlnet Contact: Tina Cheng
Clone Pre Prod | Application | Yes | 2022-08-04 21:30 | 2022-08-05 | IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install What: IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install Impact: EJQ2 will be unavailable during the outage. Contact: Michael Buechlein
Clone UAT | Application | Yes | 2022-08-05 | 2022-08-05 00:30 | IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install What: IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install Impact: EJQ2 will be unavailable during the outage. Contact: Michael Buechlein
Clone UAT | Application | No | 2022-08-05 | 2022-08-05 08:00 | Issue: connection timeouts on ALL calls from My Priorities and Starting Point (running on the DCOS DCX (critical) cluster) to any services running on the DCOS general cluster via the SSL offload farm (e.g., calls to crt-client-teams-rest-ssl, hrm-persons-svc-ssl, iaa-ejauthsvc-ssl, etc.). Fix/Root Cause: we added the new egress entry to allow communication to the Konvoy general cluster via the ssl farm to our network policy files, we were able to successfully connect to services running on the general cluster. This was required because the services on the general cluster that we could not connect to earlier have been migrated from DCOS to Konvoy. FYI, team is making a prod change this weekend to ensure that it doesn't bite them there too.
Clone Pre Prod | Application | Yes | 2022-08-05 | 2022-08-05 00:30 | IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install What: IPL of EJQ2 to new SYSRES in preparation of z/OS 2.4 install Impact: EJQ2 will be unavailable during the outage. Contact: Michael Buechlein
Clone Pre Prod | Application | No | 2022-08-05 13:07 | 2022-08-05 13:16 | Weblogic domain bounce of application2svc. Director approval provided by Blake Moyer
Development | Database | Yes | 2022-08-06 19:00 | 2022-08-07 | RHEL7 OS patching for Oracle Database servers between 8/6 - 8/7 nlddora1-1 & 2 DEVL002 EDW/DSS DEVL003 Wherescape DEVL028 ServiceCenter DEVL031 CMS DEVL041 weblogic 8 DEVL042 Asset Manager DEVL043 TSA nlddora1-3 & 4 DEVL029 Autosys DEVL030 Autosys DEVL052 ECM DEVL055 ECM / ECF DEVL058 OIMAINTG DEVL060 OIMADM DEVL142 Acct Access DEVL070 CFW, JCA, wam - Tempe DEVL075 ENT / FAST DEVL083 OIM DEVL092 Apex DEVL093 ETG nlddora1-5 & 6 DEVL101 Legal Hold DEVL105 Bondnet DEVL109 PPM DEVL108 PPM MGMT074 Foglight MGMT005 OEM13 MGMT076 RMAN Cluster 2: PSFIN nlddora2-1 & 2 DEVL115 FS92TST2 DEVL016 FS92DEV DEVL118 FS92SYST DEVL062 FS92EXT DEVL063 FS92STG nlddora2-3 & 4 DEVL126 OIC DEVL127 OIC DEVL129 OIC PS HR nlddora2-6 DEVL131 HR92SYST PS HR nlddora2-6 DEVL151 HR92EXT PS HR nlddora2-6 DEVL154 HR92TST2 PS HR nlddora2-5 DEVL152 HR92TAX PS HR nlddora2-5 DEVL153 HR92TST1 PS HR nlddora2-5 DEVL156 HR92DEV PS HR nlddora2-5 DEVL157 HR92STG Cluster 3: nlddora3-1 & 2 DEVL942 Acct Access DEVL071 avpawav DEVL069 CFW, JCA, WAM- TPE
Development | Application | Yes | 2022-08-08 21:00 | 2022-08-08 23:30 | Tentative-Batch needs to be held on EDJA for the duration of DXC change # CHG0579497 to upgrade CoZ:SFTP to v7.1.1 Impact: Batch on EDJA will be unavailable during this time. Contact: Mike Buechlein
Clone UAT | Database | Yes | 2022-08-08 09:00 | 2022-08-08 17:00 | Jumbo Frames enablement in Dev/Clone (work on remaining Oracle hosts - same as work on 8/4) What: Maintenance will be done the Non-Prod Oracle hosts listed below to increase MTU. Work will be done 1 host at a time. VMs on each host will be migrated off 1 at a time and the host will put into maintenance mode. Once work on the host is complete host will be taken out of maintenance mode and VMs will be migrated back 1 at a time. This work will be repeated for each host nedsrv83 nedsrv85 nedsrv86 nedsrv103 nedsrv81 nedsrv82 Impact: No expected impact. This work was previously done on nedsrv84 with no issues seen. Contact: Jim Moore
Clone Pre Prod | Database | Yes | 2022-08-08 09:00 | 2022-08-08 17:00 | Jumbo Frames enablement in Dev/Clone (work on remaining Oracle hosts - same as work on 8/4) What: Maintenance will be done the Non-Prod Oracle hosts listed below to increase MTU. Work will be done 1 host at a time. VMs on each host will be migrated off 1 at a time and the host will put into maintenance mode. Once work on the host is complete host will be taken out of maintenance mode and VMs will be migrated back 1 at a time. This work will be repeated for each host nedsrv83 nedsrv85 nedsrv86 nedsrv103 nedsrv81 nedsrv82 Impact: No expected impact. This work was previously done on nedsrv84 with no issues seen. Contact: Jim Moore
Clone UAT | Clone | Yes | 2022-08-09 17:00 | 2022-08-09 18:00 | Fix for IDMS data extract and db2 load jobs What: IDMS Abandonment Cluster 13 data extract & load for UAT Impact: These IDMS Abandonment Cluster 13 IDS Journal related DB2 tables will be in read-only during the outage: IDSJRNL-31415 JRNL-QTY JRNL-POSN-QTY DIST-CUSIP-NO JRNL-REVERSAL-FLAG JRNL-TYPE-CD DIST-METHOD-CD CUST-BACKUP-WITHHOLD-CD CUST-W8-CD ACCTPRB-31409 PAYABLE-DA These two related tables will also experience an outage while the data correction process is running: PMTSCHD_31406 REDISTXT_31420 Contact: IDMSAbandonment-CoreTeam
Clone Pre Prod | Application | Yes | 2022-08-09 22:00 | 2022-08-09 23:00 | Fix being installed to CA7 on Pre Prod and Q9 What: Fix being installed to CA7 on Pre Prod and Q9 Impact: CA-7 batch will be put on hold while fix is installed. No new batch allowed to run until CA-7 is back up Contact: Fred Swift
Development | Windows Servers | Yes | 2022-08-11 19:00 | 2022-08-11 21:00 | Crowdstrike Sensor Release 6.42.15610 for Win10 and WinServer Impact: Crowdstrike Sensor in place upgrades require no reboot and is transparent to the user. The user will not impact any performance issues. Post Implementation Checklist: Validate from the Crowdstrike console that all Windows Devices, sensors have been upgraded to the new version 6.42.15610 Contact: Kris Johnson (System-Security)
Clone UAT | Database | Yes | 2022-08-11 21:00 | 2022-08-12 | Apply July 2022 Oracle PSU for WebLogic to UAT CLONE What: Apply July 2022 Oracle PSU for WebLogic to UAT CLONE internal domains. Web platform team will make sure all the Pre-prod STL weblogic domains will be up and running after the change. Impact: Clone UAT -stl environment will be unavailable during this window. Contact: Kiran Chada
Clone UAT | Database | Yes | 2022-08-12 | 2022-08-12 01:00 | Apply July 2022 Oracle PSU for WebLogic to UAT CLONE What: Apply July 2022 Oracle PSU for WebLogic to UAT CLONE internal domains. Web platform team will make sure all the Pre-prod STL weblogic domains will be up and running after the change. Impact: Clone UAT -stl environment will be unavailable during this window. Contact: Kiran Chada
Clone UAT | Database | Yes | 2022-08-12 19:00 | 2022-08-13 | apply 220206 OS patch for all the Oracle database servers Oracle DBA team would like to apply the latest PS patch for some of the Oracle database servers in clone between 8/13 – 8/14. What: RHEL patching for Oracle Database Servers Cluster 1,2, Please have your applications shut down by 7pm Friday 8/12 . Impact: The following Server/Databases will be down. Clone Cluster 1: nlpdora1-1 &2 MGMT025 OEM 13c MGMT081 OEM PROD027 PPM/Jira PROD051 ECT nlpdora1-3: PROD147 OIC nlpdora1-4: PROD066 WAV Clone Cluster 2: nlpdora2-1 & 2 PROD102 Legal Hold nlpdora2-3 &4 PROD090 HR PROD096 APEX PROD106 BONDNET Contact: Marshall Major,James Cazier
Clone Pre Prod | Database | Yes | 2022-08-12 19:00 | 2022-08-13 | apply 220206 OS patch for all the Oracle database servers Oracle DBA team would like to apply the latest PS patch for some of the Oracle database servers in clone between 8/13 – 8/14. What: RHEL patching for Oracle Database Servers Cluster 1,2, Please have your applications shut down by 7pm Friday 8/12 . Impact: The following Server/Databases will be down. Clone Cluster 1: nlpdora1-1 &2 MGMT025 OEM 13c MGMT081 OEM PROD027 PPM/Jira PROD051 ECT nlpdora1-3: PROD147 OIC nlpdora1-4: PROD066 WAV Clone Cluster 2: nlpdora2-1 & 2 PROD102 Legal Hold nlpdora2-3 &4 PROD090 HR PROD096 APEX PROD106 BONDNET Contact: Marshall Major,James Cazier